## Transmittal
#VALUE! | spaceagency
DOCUMENT TRANSMITTAL
To:
Attn:
Project Title | MARGARET RIVER HOTEL
Project Number | 2101 |  | Date Issued
DRAWING REGISTER | No. | CURRENT REV | 02.04.26 | 20.04.26 | 29.04.26 | 07.05.26 | 15.05.26 | 29.05.26 | 29.06.26 | 10.07.26 | 29.07.26
A0 SITE
COVER | A000 | 07 | 02 | 03 |  | 04 | 05 | 06 | 07
SITE PLAN | A001 | 03 |  | 03
EXISTING_ GROUND FLOOR | A002 | 01
EXISTING_ FIRST FLOOR | A003 | 01
EXISTING_ ROOF | A004 | 01
DEMOLITION AND PRE-WORKS_ GROUND FLOOR | A005 | 01
DEMOLITION_ FIRST FLOOR | A006 | 01
DEMOLITION_ ROOF | A007 | 01
A1 PLANS
GROUND FLOOR | A100 | 27 |  | 25 |  |  | 26 | 27
FIRST FLOOR | A101 | 18 |  | 17 |  |  |  | 18
ATTIC _ ROOF | A102 | 03
CARPARK 2 | A103 | 08
GROUND FLOOR_FURNISHED | A110 | D
FIRST FLOOR_FURNISHED | A111 | D
GROUND FLOOR | A120 | 12
FIRST FLOOR | A121 | 07
GROUND FLOOR NORTH - CEILINGS | A140.1 | 21 |  | 17 |  |  | 18 | 19 | 20 |  | 21
GROUND FLOOR SOUTH - CEILINGS | A140.2 | 15 |  | 13 |  | 14 |  |  |  |  | 15
DOCK, STAFF AMENITIES - CEILINGS | A140.3 | 12 |  | 10 |  |  | 11 |  |  |  | 12
FIRST FLOOR CEILINGS (HERITAGE WING) | A141.1 | 10 |  | 9 |  |  |  |  | 10
FIRST FLOOR CEILINGS (1980s WING) | A141.2 | 01 | [8 empty] | 01
FIRST FLOOR CEILINGS (NEW WING) | A141.3 | 13 | 10 |  |  |  | 11 | 12 |  |  | 13
CARPARK CEILING | A142 | 07 |  | 05 |  | 06 |  | 07
GROUND FLOOR LIGHTING | A160 | F
FIRST FLOOR LIGHTING | A161 | F
A2 ELEVATIONS
ELEVATIONS | A201 | 07 |  | 06 |  |  |  | 07
ELEVATIONS | A202 | 10 |  | 08 |  |  | 09 | 10
ELEVATIONS | A203 | 07 | [5 empty] | 07
TIMBER SCREENS | A204 | 04
CLADDING SETOUT | A205 | 03
A3 SECTIONS
SECTION A | A301 | 03
SECTION B | A302 | 03
SECTIONS C, D | A303 | 03
SECTION E | A304 | 04
SECTION F | A305 | 03
SECTIONS G, H | A306 | 04
SECTION I, J, K | A307 | 02
A4 STAIRS
STAIR 1 - MAIN ENTRANCE | A401 | 02 |  | 02
STAIR 2 | A402 | 02 |  |  |  |  | 02
STAIR 3 | A403 | 05 |  | 03 |  | 04 |  |  | 05
STAIR 4, 5, 6 | A404 | 01
A5 DETAILS
WALL TYPES | A501 | 01
TIMBER SCREEN SETOUT DETAILS | A502 | 01
TYPICAL DOOR DETAILS | A503 | 03
TYPICAL DOOR DETAILS | A504 | 4
GATE DETAILS | A505 | 01
GF PLAN DETAILS | A511 | 00
L1 PLAN DETAILS | A512 | 01
L1 PLAN DETAILS | A513 | 01
L1 PLAN DETAILS | A514 | 02
L1 PLAN DETAILS | A515 | 01
DOOR INTERFACE DETAILS | A516 | 01
TIMBER SCREEN + FACADE DETAILS | A551 | 01
SECTION DETAILS | A552 | 03
SECTION DETAILS | A553 | 01
SECTION DETAILS | A554 | 02
SECTION DETAILS | A555 | 02
SECTION DETAILS | A556 | 01
A6 ROOM LAYOUTS
ENTRANCE, RECEPTION, PARLOUR - PLANS | A601 | 05 | [8 empty] | 05
BERNARDS BAR - PLAN | A601.1 | 04 | [5 empty] | 3 |  |  | 04
CONSERVATORY - PLAN | A601.2 | 3
ENTRY & RECEPTION - ELEVATIONS | A602 | 10 |  | 08 |  |  | 09 |  | 10
PARLOUR ELEVATIONS | A603 | 4 |  |  |  |  | 4
BERNARDS BAR - ELEVATIONS 1_2 | A604 | 5 |  | 5
BERNARDS BAR - ELEVATIONS 2_2 | A605 | 04 | [5 empty] | 3 |  |  | 04
BERNARDS BAR - DETAILS 1_4 | A606 | 0
BERNARDS BAR - DETAILS 2_4 | A606.1 | 0
BERNARDS BAR - DETAILS 3_4 | A606.2 | 0
BERNARDS BAR - DETAILS 4_4 | A606.3 | 0
CONSERVATORY - ELEVATIONS | A607 | 05 | [5 empty] | 4 |  |  | 05
MULTIPURPOSE ROOM, WINE LIBRARY - PLANS | A609 | 4
EAST ENTRY, OFFICE, GLASS WASH - PLANS | A609.1 | 02 | [5 empty] | 02
WINE TASTING_ VAULT - ELEVATIONS | A610 | 06 | [8 empty] | 06
WINE LIBRARY DETAILS | A610.1 | 01
MULTIPURPOSE ROOM - ELEVATIONS | A612 | 5
EAST ENTRY, LOBBY & GLASS WASH - ELEVATIONS | A614 | 02 | [6 empty] | 02
LIFT LOBBY - ELEVATIONS | A615 | 03 | [6 empty] | 03
FUNCTION AMENITIES | A616 | 03 | [6 empty] | 02 |  | 03
BERNARDS BAR AMENITIES - PLAN AND ELEVATIONS | A617 | 01 | [6 empty] | 01
BERNARD'S CORNER AMENITIES - ELEVATIONS | A617.1 | 01 | [6 empty] | 01
KITCHEN - PLAN | A618 | 05
KITCHEN - ELEVATIONS | A618.1 | 07 |  |  |  |  | 6 |  | 07
DOCK, STAFF AMENITIES - PLAN AND ELEVATIONS | A619 | 03
GUEST WC, MUDROOM - ELEVATIONS | A620 | 0
GUEST CORRIDOR (HERITAGE WING) | A621 | 3 | [5 empty] | 3
GUEST CORRIDOR (HERITAGE WING) | A621.1 | 2
BUREAU, GUEST VALET & LARDER | A622 | 03
GUEST LANDING L1 & L2 | A624 | 05
HERITAGE ROOM 101 | A625 | 8 |  |  |  | 7 |  | 8
HERITAGE ROOM 102 | A626 | 5
HERITAGE ROOM 102 | A627 | 4 | [5 empty] | 4
HERITAGE ROOM 103 | A627.2 | 5
HERITAGE ROOM 104 | A628 | 4 | [5 empty] | 4
HERITAGE ROOM 105 | A629 | 6 | [5 empty] | 6
HERITAGE ROOM 106 | A630 | 4 | [5 empty] | 4
HERITAGE ROOMS 107, 108 | A631 | 6 |  |  |  |  | 5 | 6
HERITAGE ROOMS 109, 110, 111 | A632 | 4
HERITAGE ROOMS 109, 110, 111 (CONTINUED) | A632.1 | 3 |  | 2 |  |  |  | 3
HERITAGE ROOM 112 (UA & NIGHT MANAGER) | A633 | 06 | [5 empty] | 5 | 06
GUEST CORRIDOR (NEW WING) | A634 | 2
GUEST CORRIDOR (NEW WING) | A634.1 | 1
NEW ROOMS - TYPE A+ (210, 212, 215, 217) | A635 | 6 |  |  |  |  | 6
NEW ROOMS - TYPE A+ UA (203 UA) | A636 | 05 | [5 empty] | 05
NEW ROOMS - TYPE A (209, 211, 214, 216) | A637 | 6 |  |  |  |  | 5 | 6
NEW ROOM - TYPE B (201, 202, 204, 205, 206, 207, 208) | A638 | 5 |  |  |  |  | 5
WALL PANELING TYPES | A651 | 0
TYP JNERY DETAILS | A652 | 0
TYP TILING DETAILS | A653 | 0
A7 DOOR AND WINDOWS
DOOR AND WINDOW LEGEND | A700 | 00 |  | 01 |  |  |  | 00
WINDOW SCHEDULE (W01-W10) | A702 | 04 |  | 03 |  |  |  | 04
WINDOW SCHEDULE (W21-W29) | A703 | 06 |  | 05 |  |  |  | 06
WINDOW SCHEDULE (W31-W39) | A704 | 06 |  | 05 |  |  |  | 06
DOOR SCHEDULE (D1-D16) | A712 | 06 |  | 05 |  |  |  | 06
DOOR SCHEDULE (D21-D39) | A713 | 07 |  | 06 |  |  |  | 07
DOOR SCHEDULE (D41-D53) | A714 | 07 |  | 06 |  |  |  | 07
DOOR TYPES (SPECIALTY DOORS) | A717 | 06 |  | 06
A8 SCHEDULES
FINISHES AND MATERIALS SCHEDULE | A801 | 18 |  |  |  | 15 | 16 | 17 | 18
FIXTURES, FITTINGS, ACCESSORIES SCHEDULE | A802 | 11 |  |  |  |  | 10 | 11
SIGNAGE SCHEDULE | A804
DOOR AND WINDOW HARDWARE SCHEDULE | A805 | 02 | [5 empty] | 02
ELECTRICAL FIXTURES | A808 | 00 |  | N |  |  |  | 00
A9 EXTERNAL WORKS
EXTERNAL WORKS PLAN | A901 | 10 |  |  | 08 |  | 09 | 10
EXTERNAL WORKS SECTIONS | A902 | 00
EXTERNAL WORKS - FENCE | A903 | 02 |  |  |  | 02
EXTERNAL WORKS DETAILS | A904 | 03 |  | 02 | [6 empty] | 03
OUTDOOR FIREPLACE BBQ | A905 | 00
EXTERNAL WORKS - GATES | A906 | 04 |  |  |  | 04
Distribution
Method of Issue: C - CD-Rom; E - Email; P - Post/Courier; U - Upload; H - Hardcopy
Purpose of Issue: A - Approval; B - Building Permit; C - Construction; F - Forward Works; I - Information; R - Review; T - For Tender; P - Preliminary
Issued by:

## Notes
MARGARET RIVER HOTEL — Architectural Drawing Issue Register (DRAFT)
How this was built
Auto-generated from the project issue folders in OneDrive:
• Rows = current architectural drawings in __CURRENT DOCUMENTS/ARCHITECT (127 sheets).
• Columns = each dated issue folder (YYMMDD_...) — the revision issued at that date.
• Revisions read from filenames: <No>_<Rev> <Name>.pdf.
To refine manually
• Fill To / Attn / Transmittal no. / Distribution / Method / Purpose / Issued by.
• Revision notes (per drawing per rev) are NOT yet captured — these live on the titleblock
revision history and would be added in a later pass (or from ArchiCAD change descriptions).
• Font is set to KMR Waldenburg Buch Halbschmal; adjust the weight if you meant a different cut.
• Black & white only, as requested. Add the spA logo in the title band.
Flags — filenames missing a revision ID (user errors to correct at source):
⚠ 260710_Liquor Licence Areas/A110 GROUND FLOOR_FURNISHED _Insurance.pdf
⚠ 260710_Liquor Licence Areas/A110 GROUND FLOOR_FURNISHED.pdf
⚠ 260710_Liquor Licence Areas/A111 FIRST FLOOR_FURNISHED _ Insurance.pdf
⚠ 260710_Liquor Licence Areas/A111 FIRST FLOOR_FURNISHED.pdf
⚠ A8 Schedules/A804 SIGNAGE SCHEDULE.pdf
Issued but not in current set (check if superseded/renamed):
• A701
• A705
• A711
• A715
• A716
• A718
• A721